## excel-1
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 42 | 47.1 | 43.7
Planned Time | 0.17083 |  | 1899-12-31 00:06
Actual Tiempo |  | 0.22569 | 1899-12-31 13:37
CPI (Cost-Performance Index) |  |  | 0.64
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 10.1 | 3.92 | 9.13
Total Defects/KLOC or equivalent | 18.7 | 7.84 | 17
Yield % | 48% | 50% | 48.1%
Code Review Rate | 2388 | 1700 | 2293
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:07 PM el 24/03/2017